## Summary
BidBrief Analysis Report
Project: | 2026 Large Sanitary Trunk Inspection Areas 4,5,6
Location: | Eagan, Minnesota
Owner: | City of Eagan
Document Pages: | 188
Analysis Statistics
Total Questions: | 91
Questions Answered: | 63
Answer Rate: | 69%
Average Confidence: | 93%
Processing Time: | 47 minutes
Analysis Date: | January 27, 2026
Key Project Requirements
Timeline: | March 1, 2026 - October 1, 2026
Scope: | ~40,000 LF of 15" to 30" sanitary sewer
Bid Deadline: | February 6, 2026 at 10:00 AM
Payment: | 95% progress payments, 5% retention
Warranty: | 2 years post-completion
Liquidated Damages: | $250/day for delays
Bonding: | Bid bond + Performance/Payment bonds
Certifications: | NASSCO PACP required for operators

## Detailed Results
Section | Question ID | Question | Answer | Confidence | Pages | Footnote
General Project Information | Q1 | What is the project name and location? | The project name is '2026 Large Sanitary Trunk Inspection Areas 4,5,6' and it is located in 'Eagan' <PDF pg 1, 2> | 100% | 1, 2 | Found on <PDF pg 1, 2>, Project Title and Notice of Request for Quotes: This information is critical for identifying the project scope and geographical area for potential bidders.
General Project Information | Q2 | What is the total project duration or timeline? | The total project duration is from 'on or after March 1st, 2026' to 'on or before October 1st, 2026' <PDF pg 2> | 100% | 2 | Found on <PDF pg 2>, Section 4: Schedule. This timeline is crucial for bidders to plan resources and ensure timely project delivery.
General Project Information | Q3 | What is the total linear footage of pipe to be rehabilitated? | The total linear footage of pipe to be rehabilitated is 'approximately 40,000 feet' <PDF pg 2, 5, 24> | 100% | 2, 5, 24 | Found on <PDF pg 2>, Section 1: Scope. Accurate measurement is essential for cost estimation and resource allocation. ¦ Found on <PDF pg 5>, Advertisement for Bids: Essential for calculating labor and material requirements. ¦ Found on <PDF pg 24>, Contract details section: Accurate footage is essential for cost estimation and resource planning.
General Project Information | Q4 | What pipe sizes (diameters) are included in the project? | The pipe sizes included in the project range from '15 inches to 30 inches' in diameter <PDF pg 2, 5, 24, 132> | 100% | 2, 5, 24, 132 | Found on <PDF pg 2>, Section 1: Scope. Knowing the pipe sizes is vital for selecting appropriate cleaning and televising equipment. ¦ Found on <PDF pg 5>, Advertisement for Bids: Critical for equipment selection and cost estimation. ¦ Found on <PDF pg 24>, Contract details section: Understanding pipe sizes is crucial for equipment selection and bid accuracy. ¦ Found on <PDF pg 132>, Section 1.01: Project Information. Correct pipe sizing is vital for equipment selection and bid accuracy.
General Project Information | Q5 | What is the project budget or estimated cost? | The project budget or estimated cost is not specified, only that 'The City shall pay Contractor for completion of the work in accordance with the Contract Documents in the amount of $' with no amount provided <PDF pg 26> | 50% | 26 | Found on <PDF pg 26>, Article III: The lack of a specified amount can affect financial planning and bid competitiveness.
General Project Information | Q6 | What are the submission deadlines for bids or proposals? | Submission deadlines for quotes are 'February 6th, 2026 10:00 AM' <PDF pg 3> | 100% | 3 | Found on <PDF pg 3>, Section 13: Timeline. Meeting submission deadlines is critical for bid consideration.
General Project Information | Q7 | Who is the project owner or contracting authority? | The project owner is the 'City of Eagan' <PDF pg 2, 40> | 100% | 2, 40 | Found on <PDF pg 2>, Section 3: Owner. Identifying the contracting authority is essential for communication and contract management. ¦ Found on <PDF pg 40>, Notice to Proceed: Identifying the project owner is essential for communication and contractual obligations.
General Project Information | Q8 | Are there any pre-bid meetings or site visits scheduled? | A pre-bid conference will not be conducted for this Project. <PDF pg 8> | 100% | 8 | Found on <PDF pg 8>, Article 4.01: The absence of a pre-bid conference implies bidders must independently review the site and documents.
General Project Information | Q9 | What bonding and insurance requirements are specified? | The bonding requirements include a "Bid Bond (Penal Sum Form)" and the need for "performance and payment bonds" <PDF pg 22, 23, 24> | 100% | 22, 23, 24 | Found on <PDF pg 22, 23, 24>, Bonding sections: Bonding is crucial for ensuring project completion and financial security.
General Project Information | Q10 | What payment terms and schedule are outlined? | Payment terms include 'Partial Payments' and 'Final Payment' with progress payments 'in an amount equal to ninety-five percent (95%) of the work completed' <PDF pg 27> | 100% | 27 | Found on <PDF pg 27>, Article IV: Understanding payment terms is critical for cash flow management and financial planning in bids.
Televising Requirments | Q11 | What resin type is required (polyester, vinyl ester, epoxy)? | NOT FOUND | - | -
Televising Requirments | Q12 | What ASTM standards apply to the CIPP materials? | NOT FOUND | - | -
Televising Requirments | Q13 | What is the required design thickness of the liner? | NOT FOUND | - | -
Televising Requirments | Q14 | What flexural strength requirements are specified? | NOT FOUND | - | -
Televising Requirments | Q15 | What flexural modulus requirements are specified? | NOT FOUND | - | -
Televising Requirments | Q16 | Are there any specific felt material requirements? | NOT FOUND | - | -
Televising Requirments | Q17 | What are the chemical resistance requirements? | NOT FOUND | - | -
Televising Requirments | Q18 | Are there specific requirements for liner permeability? | NOT FOUND | - | -
Televising Requirments | Q19 | What certification or testing documentation is required for materials? | The document requires submission of a "valid copy of the NASSCO PACP Operators Certificate for each operator" <PDF pg 150> | 90% | 150 | Found on <PDF pg 150>, Section 1.05: Submittals include certification documentation for operators, ensuring qualified personnel conduct inspections.
Televising Requirments | Q20 | Are there any material submittal or approval requirements? | The document states that "Contractor shall provide all data in support of any proposed 'or equal' item at Contractor's expense" and "No 'or-equal' item will be ordered, furnished, installed, or utilized until Engineer's review is complete" <PDF pg 74> | 90% | 74 | Found on <PDF pg 74>, Section 7.05: The section details the process for 'or equal' item submissions and approvals, relevant for ensuring compliance with material specifications.
Televising Requirments | Q21 | Inspection Requirments | NOT FOUND | - | -
Access to easement | Q21 | What installation method is specified (inversion, pull-in-place, other)? | NOT FOUND | - | -
Access to easement | Q22 | What curing method is required (steam, hot water, UV, ambient)? | NOT FOUND | - | -
Access to easement | Q23 | What are the minimum and maximum curing temperature requirements? | NOT FOUND | - | -
Access to easement | Q24 | What is the required curing duration? | NOT FOUND | - | -
Access to easement | Q25 | Are there specific requirements for pre-installation cleaning or inspection? | The project requires "cleaning and televising 15-inch to 30-inch sanitary sewer" and "manually review televising data and grace according to NASSCO standards" <PDF pg 2> | 100% | 2 | Found on <PDF pg 2>, Project Information and Requirements Section 1: Cleaning and televising are essential pre-installation steps.
Access to easement | Q26 | What bypass pumping requirements are specified? | The document specifies that "Payment for TV inspection of siphon shall include any dewatering, excluding bypass pumping." <PDF pg 149> | 100% | 149 | Found on <PDF pg 149>, Section 1.02 A.4: Dewatering is required for clear inspection, but bypass pumping is not included. Bidders must account for this in their cost estimates.
Access to easement | Q27 | Are there specific requirements for service lateral reconnections? | NOT FOUND | - | -
Access to easement | Q28 | What end seal requirements are specified? | NOT FOUND | - | -
Access to easement | Q29 | Are there manhole-to-manhole or continuous lining requirements? | The document specifies that "Survey television inspection videos shall be continuous for pipe segments between manholes." <PDF pg 154> | 100% | 154 | Found on <PDF pg 154>, Section 3.03: Continuous video inspection is required, impacting video recording and data management.
Access to easement | Q30 | What are the requirements for monitoring curing parameters? | NOT FOUND | - | -
Safety & Environmental Compliance | Q41 | What confined space entry requirements are specified? | NOT FOUND | - | -
Safety & Environmental Compliance | Q42 | What traffic control and road closure requirements exist? | The document specifies to 'Maintain existing roads' and 'Provide detours necessary for unimpeded traffic flow' <PDF pg 144> | 90% | 144 | Found on <PDF pg 144>, Section 01 5000: Temporary Facilities and Controls. Coordination with governing authorities is implied for compliance.
Safety & Environmental Compliance | Q43 | Are there specific OSHA or safety plan requirements? | The document states that the "Contractor shall comply with all applicable Laws and Regulations relating to the safety of persons or property" and must "erect and maintain all necessary safeguards for such safety and protection." <PDF pg 79> | 90% | 79 | Found on <PDF pg 79>, Section 7.13: General safety compliance requirements are outlined, impacting contractor's safety plan development.
Safety & Environmental Compliance | Q44 | What environmental permits or compliance requirements are needed? | The CONTRACTOR shall secure 'all other federal, state, county, and City permits necessary for construction.' <PDF pg 3> | 90% | 3 | Found on <PDF pg 3>, Permits/Inspections: General requirement for securing necessary permits.
Safety & Environmental Compliance | Q45 | Are there odor control or emission requirements during curing? | NOT FOUND | - | -
Safety & Environmental Compliance | Q46 | What waste disposal requirements are specified? | CONTRACTOR to 'remove all debris, containers and scrap materials from the project site and dispose of in a legal manner.' <PDF pg 3> | 95% | 3 | Found on <PDF pg 3>, Clean up: Specifies legal disposal of debris and materials.
Safety & Environmental Compliance | Q47 | Are there noise or working hours restrictions? | The document specifies "Regular working hours will be 7:30 A.M. to 6:00 P.M. Monday – Friday." <PDF pg 123> | 95% | 123 | Found on <PDF pg 123>, Section 7.03: Working hours are specified, implying noise restrictions outside these times.
Safety & Environmental Compliance | Q48 | What emergency response procedures are required? | Contractor must "immediately: (1) secure or otherwise isolate such condition; (2) stop all Work in connection with such condition" if a Hazardous Environmental Condition is encountered. <PDF pg 65> | 95% | 65 | Found on <PDF pg 65>, Section 5.06.E: Details emergency procedures for hazardous conditions.
Safety & Environmental Compliance | Q49 | Are there specific requirements for protecting water quality? | Conduct work in a manner that avoids interruption of effective collection system operation. Prevent the bypass of untreated wastewaters to surface water or drainage ways. <PDF pg 133> | 90% | 133 | Found on <PDF pg 133>, Section 1.06: Continuity of treatment system operation. Critical for maintaining environmental compliance.
Safety & Environmental Compliance | Q50 | What personal protective equipment (PPE) is mandated? | NOT FOUND | - | -
Equipment & Resource Requirements | Q51 | What specific equipment or machinery is required for the project? | The project requires the use of a 'pan-and-tilt radial-viewing pipe inspection camera that pans ± 275 degrees and rotates 360 degrees' along with a 'lighting system that allows the features and condition of the pipe to be clearly seen.' <PDF pg 152> | 100% | 152 | Found on <PDF pg 152>, Section 2.01: Video Equipment. This is crucial for ensuring accurate inspection results and compliance with project standards.
Equipment & Resource Requirements | Q52 | Are there minimum crew size or staffing requirements? | The document specifies that "The Contractor or competent Superintendent must be on the Project when construction activities are taking place." <PDF pg 132> | 85% | 132 | Found on <PDF pg 132>, Section 1.03 A: Superintendent presence is mandatory, impacting mobilization and staffing plans.
Equipment & Resource Requirements | Q53 | What certification or training requirements exist for operators? | Operators must have a 'valid copy of the NASSCO PACP Operators Certificate' <PDF pg 150> | 100% | 150 | Found on <PDF pg 150>, Section 1.05 C: Certification ensures standardization and consistency in pipeline condition assessment, critical for bid compliance.
Equipment & Resource Requirements | Q54 | Are there backup equipment or redundancy requirements? | NOT FOUND | - | -
Equipment & Resource Requirements | Q55 | What boiler or heating system specifications are required? | The contractor is required to provide and pay for heat devices and heat as needed to maintain specified conditions for construction operations. "Contractor shall provide and pay for heat devices and heat as required to maintain specified conditions for construction operations." <PDF pg 144> | 90% | 144 | Found on <PDF pg 144>, Section 01 5000, 1.03: Temporary heat provision is the contractor's responsibility, impacting cost estimates and logistical planning.
Equipment & Resource Requirements | Q56 | Are there specific camera or inspection equipment requirements? | The camera must provide 'quality sufficient to evaluate the condition of the sanitary sewer' and videos should be in 'MPEG4 format' with 'a resolution of at least 480 pixels' <PDF pg 150> | 100% | 150 | Found on <PDF pg 150>, Section 1.05 D: Ensures video quality for accurate assessment, impacting equipment selection in bids.
Equipment & Resource Requirements | Q57 | What staging area or work site requirements exist? | The document specifies the need for maintaining vehicular access and parking, including constructing and maintaining temporary roads and providing temporary parking areas. "Maintain existing roads. Coordinate access and haul routes with governing authorities and Owner. Construct and maintain temporary roads accessing public thoroughfares to serve construction area." <PDF pg 144> | 95% | 144 | Found on <PDF pg 144>, Section 01 5000, 1.06: Vehicular access and parking are crucial for site operations, affecting traffic management and site layout planning.
Equipment & Resource Requirements | Q58 | Are there utility locating or coordination requirements? | The document outlines the contractor's responsibilities for 'reviewing and checking all information and data regarding existing Underground Facilities at the Site' and 'coordination of the Work with the owners (including Owner) of such Underground Facilities, during construction.' <PDF pg 63> | 100% | 63 | Found on <PDF pg 63>, Section 5.05.A: Contractor must coordinate with utility owners, which is crucial for avoiding conflicts during construction.
Equipment & Resource Requirements | Q59 | What water supply or discharge requirements are specified? | The document advises to 'use an appropriately sized backflow preventer as required by the City of Eagan Water Department when drawing water from a public hydrant.' <PDF pg 153> | 100% | 153 | Found on <PDF pg 153>, Section 3.02: Preparation. This is important for maintaining public health and safety standards.
Equipment & Resource Requirements | Q60 | Are there specific requirements for monitoring equipment during curing? | NOT FOUND | - | -
Warranty & Project Closeout | Q61 | What warranty period is required for the CIPP installation? | The warranty period required is '2 years after Substantial Completion.' <PDF pg 119> | 100% | 119 | Found on <PDF pg 119>, Article 6.01: This warranty period is critical for ensuring long-term performance and compliance with contract terms.
Warranty & Project Closeout | Q62 | What items or defects are covered under warranty? | Items or defects covered under warranty include "defective Work" and "defective repairs to the Site or adjacent areas" <PDF pg 111> | 95% | 111 | Found on <PDF pg 111>, Section 15.08.A: Defective work and repairs are covered. Important for ensuring quality assurance and compliance with contract specifications.
Warranty & Project Closeout | Q63 | What as-built documentation is required at project completion? | Contractor shall maintain in a safe place at the Site one printed record copy of all Drawings, Specifications, Addenda, Change Orders, Work Change Directives, Field Orders, written interpretations and clarifications, and approved Shop Drawings. Contractor shall keep such record documents in good order and annotate them to show changes made during construction. These record documents, together with all approved Samples, will be available to Engineer for reference. Upon completion of the Work, Contractor shall deliver these record documents to Engineer. <PDF pg 78> | 95% | 78 | Found on <PDF pg 78>, Section 7.12: Record Documents. This is crucial for project closeout and ensuring all changes are documented.
Warranty & Project Closeout | Q64 | Are there O&M (Operations & Maintenance) manual requirements? | O&M manual requirements include "maintenance and operating instructions" <PDF pg 109> | 90% | 109 | Found on <PDF pg 109>, Section 15.06.A.1: O&M manuals are critical for operational readiness and training. Verify completeness before project handover.
Warranty & Project Closeout | Q65 | What final testing or certification deliverables are required? | Contractor shall give Engineer timely notice of readiness of the Work (or specific parts thereof) for all required inspections and tests, and shall cooperate with inspection and testing personnel to facilitate required inspections and tests." <PDF pg 101> | 90% | 101 | Found on <PDF pg 101>, Article 14.02: Details the contractor's obligations for facilitating inspections and tests.
Warranty & Project Closeout | Q66 | Are there record drawing or GIS data submission requirements? | Updated or modified GIS data shall be submitted in an ESRI shapefile or geodatabase format that is compliant with ArcGIS version 10.2 or higher. <PDF pg 151> | 95% | 151 | Found on <PDF pg 151>, Section G: GIS Data requirements are crucial for maintaining accurate project records.
Warranty & Project Closeout | Q67 | What site restoration or cleanup requirements exist? | The CONTRACTOR is required to "clean up finished surfaces, storage areas and areas contiguous to the work. Remove all debris, containers and scrap materials from the project site and dispose of in a legal manner. Touch up and restore anything that is damaged prior to final inspection." <PDF pg 3> | 100% | 3 | Found on <PDF pg 3>, Section 10: Cleanup requirements are clearly specified, impacting project closeout procedures.
Warranty & Project Closeout | Q68 | Are there final inspection or acceptance procedures specified? | Final inspection procedures include "a final inspection with Owner and Contractor" and notification of incomplete or defective work <PDF pg 109> | 95% | 109 | Found on <PDF pg 109>, Section 15.05.A: Final inspection procedures ensure project completion and quality assurance. Coordinate with stakeholders for timely inspection.
Warranty & Project Closeout | Q69 | What retention or liquidated damages provisions are included? | The document states, "as liquidated damages for delay or loss of grant funds (but not as a penalty), Contractor shall pay $250 each day that expires after the time specified for completion and readiness for final payment." <PDF pg 26> | 100% | 26 | Found on <PDF pg 26>, Article II.2: Liquidated damages clause specifies financial penalties for project delays, impacting bidder's risk assessment.
Warranty & Project Closeout | Q70 | Are there close-out meeting or final presentation requirements? | NOT FOUND | - | -
Special Conditions & Constraints | Q71 | Are there specific working depth or elevation constraints? | The document specifies that the 'depth of wastewater flow' must not exceed certain percentages based on 'Pipe Diameter (Inches)' during inspection: '6 - 10' inches at '10%', '12 - 24' inches at '15%', and 'Over 24' inches at '20%'. <PDF pg 155> | 90% | 155 | Found on <PDF pg 155>, Section 3.04: These constraints are vital for ensuring accurate television inspection and preventing equipment damage.
Special Conditions & Constraints | Q72 | What groundwater or high water table conditions exist? | The document mentions 'differing subsurface or physical condition' but does not specify groundwater or high water table conditions. <PDF pg 58> | 20% | 58 | Found on <PDF pg 58>, Article 5. Delays due to subsurface conditions are mentioned, but not specific to groundwater.
Special Conditions & Constraints | Q73 | Are there adjacent structure or utility protection requirements? | The document specifies that 'Special care shall be taken to prevent damage to all trees, pavement, and curb and gutter.' <PDF pg 2> | 90% | 2 | Found on <PDF pg 2>, Section 7: Special site conditions. This implies a requirement for careful handling to avoid damage during the project.
Special Conditions & Constraints | Q74 | What prevailing wage or labor requirements apply? | The document specifies that the Contractor must 'promptly make payment to all claimants' for labor and materials used in the project <PDF pg 36> | 80% | 36 | Found on <PDF pg 36>, Section 1: Labor and Material Payment Bond. This section implies adherence to labor payment standards but does not explicitly mention prevailing wage laws.
Special Conditions & Constraints | Q75 | Are there DBE/MBE/WBE participation requirements? | NOT FOUND | - | -
Special Conditions & Constraints | Q76 | What American-made or Buy America requirements exist? | NOT FOUND | - | -
Special Conditions & Constraints | Q77 | Are there specific sequencing or phasing requirements? | The Contractor shall "construct Work in stages to accommodate Owner's occupancy and operational requirements during the construction period." <PDF pg 133> | 90% | 133 | Found on <PDF pg 133>, Section 1.09: Work Sequence. Critical for planning construction phases in the bidding process.
Special Conditions & Constraints | Q78 | What coordination with other contractors or projects is required? | The Contractor must 'notify Owner; the owners of adjacent property; the owners of Underground Facilities and other utilities' and 'cooperate with them in the protection, removal, relocation, and replacement of their property or work in progress.' <PDF pg 79> | 90% | 79 | Found on <PDF pg 79>, Section 7.13.F: Coordination with adjacent property and utility owners is essential for project execution.
Special Conditions & Constraints | Q79 | Are there historic preservation or archeological requirements? | NOT FOUND | - | -
Special Conditions & Constraints | Q80 | What pandemic or health-related protocols are specified? | The CONTRACTOR shall be thoroughly familiar with all phases of sewer pipe and structure cleaning to ensure the completion of this Contract without causing a health hazard or damage to the sewage system, public, and private properties. <PDF pg 159> | 70% | 159 | Found on <PDF pg 159>, Section 3.01: Emphasizes health and safety in operations, potentially relevant to pandemic protocols.
Pricing Structure & Payment | Q81 | What unit pricing structure is required (per linear foot, lump sum)? | Bidders must submit a Bid on a unit price basis for each item of Work listed in the unit price section of the Bid Form. <PDF pg 14> | 100% | 14 | Found on <PDF pg 14>, Article 13.01: Unit Price. This indicates that the pricing structure is per unit, likely per linear foot, which is typical for trunk line projects.
Pricing Structure & Payment | Q82 | Are there separate bid items for different pipe diameters? | Payment for video inspection is based on 'bid item for TV Inspection of appropriate line size.' <PDF pg 149> | 100% | 149 | Found on <PDF pg 149>, Section 1.02 A.2: This suggests that different pipe diameters have distinct bid items, affecting how bids are structured.
Pricing Structure & Payment | Q83 | What mobilization or demobilization costs are allowed? | Mobilization/Demobilization costs are allowed as a lump sum item. 'Item No. 1 Mobilization/Demobilization LS 1 $' <PDF pg 17> | 100% | 17 | Found on <PDF pg 17>, Article 3.01: Unit Price Bids. Mobilization/Demobilization is a standard line item in construction bids, covering initial project setup costs.
Pricing Structure & Payment | Q84 | Are there allowances or contingencies included in the bid? | The document includes 'Owner's Contingency Allowance' for unanticipated costs. <PDF pg 100> | 90% | 100 | Found on <PDF pg 100>, Section 13.02.C: Contingency allowances are for Owner's use, relevant for cost management in bids.
Pricing Structure & Payment | Q85 | What payment retention percentage is specified? | The payment retention percentage specified is "five (5) percent of the amount due the Contractor on account of progress payments." <PDF pg 136> | 100% | 136 | Found on <PDF pg 136>, Section 1.03: Retainage ensures proper contract performance by withholding a percentage of progress payments.
Pricing Structure & Payment | Q86 | How frequently will progress payments be made? | Progress payments will be made on a "Calendar Month" basis, with applications submitted "on the first day of the month." <PDF pg 136> | 100% | 136 | Found on <PDF pg 136>, Section 1.02: Payment procedures require monthly submissions for progress payments.
Pricing Structure & Payment | Q87 | Are there incentive or penalty clauses related to schedule? | There is a penalty clause for delays, with liquidated damages of "$250 each day" <PDF pg 26> | 95% | 26 | Found on <PDF pg 26>, Article II.2: Liquidated damages clause incentivizes timely completion and mitigates financial risk for the City.
Pricing Structure & Payment | Q88 | What documentation is required for payment applications? | The documentation required for payment applications includes "lien waivers, sales tax statements, and other required submittals." <PDF pg 136> | 100% | 136 | Found on <PDF pg 136>, Section 1.05: Final payment requires specific documentation to ensure compliance with contract terms.
Pricing Structure & Payment | Q89 | Are there value engineering or cost savings provisions? | NOT FOUND | - | -
Pricing Structure & Payment | Q90 | What change order procedures and pricing are outlined? | Change order procedures involve the Contractor submitting "a firm proposal for changes in the Contract Sum and Contract Time" upon notification of desired changes by the Owner. <PDF pg 136-137> | 100% | 136, 137 | Found on <PDF pg 136-137>, Section 1.06: Change orders require detailed proposals from the Contractor for Owner's consideration.
Cleaning Requirments | Q91 | What minimum years of CIPP experience are required? | NOT FOUND | - | -
Cleaning Requirments | Q92 | Are there specific project size or complexity requirements for experience? | NOT FOUND | - | -
Cleaning Requirments | Q93 | How many project references are required? | The letter shall include: "References where the CONTRACTOR has used the identified cleaning method successfully within the past three (3) years projects with sanitary sewer pipes similar in diameter, length, type, age, and condition." <PDF pg 158> | 90% | 158 | Found on <PDF pg 158>, Section 1.03: Submittals. This is crucial for assessing contractor's past performance.
Cleaning Requirments | Q94 | What licensing or certification is required for the contractor? | The Bid must contain evidence of Bidder's authority to do business in the state where the Project is located, or Bidder must certify in writing that it will obtain such authority within the time for acceptance of Bids and attach such certification to the Bid. If Bidder is required to be licensed to submit a Bid or perform the Work in the state where the Project is located, the Bid must contain evidence of Bidder's licensure, or Bidder must certify in writing that it will obtain such licensure within the time for acceptance of Bids and attach such certification to the Bid. Bidder's state contractor license number, if any, must also be shown on the Bid Form." <PDF pg 14> | 100% | 14 | Found on <PDF pg 14>, Article 12.11 and 12.12: Licensing and business authority are prerequisites for bid acceptance.
Cleaning Requirments | Q95 | Are there financial capacity or bonding limitations? | A Bid must be accompanied by Bid security made payable to Owner in an amount of 5 percent of Bidder's maximum Bid price. <PDF pg 11> | 90% | 11 | Found on <PDF pg 11>, Article 8.01: Bid security requirements indicate financial capacity considerations for bidders.
Cleaning Requirments | Q96 | What key personnel qualifications and resumes are required? | The document specifies that "The Contractor or competent Superintendent must be on the Project when construction activities are taking place." <PDF pg 132> | 80% | 132 | Found on <PDF pg 132>, Section 1.03: Quality Assurance. Superintendent presence is mandatory for project oversight.
Cleaning Requirments | Q97 | Are there manufacturer certification or training requirements? | The document requires NASSCO PACP certification for inspection software and operators. "Inspection Software must be NASSCO PACP Certified and proof of certification of Software shall be submitted prior to commencing the work." <PDF pg 150> | 100% | 150 | Found on <PDF pg 150>, Section 1.05: Certification ensures compliance with industry standards for pipeline assessment.
Cleaning Requirments | Q98 | What safety record or EMR (Experience Modification Rate) requirements exist? | NOT FOUND | - | -
Cleaning Requirments | Q99 | Are there prequalification or qualification statement requirements? | The document states that "Responsible Contractor Verification Form" is part of the contract documents. <PDF pg 3> | 70% | 3 | Found on <PDF pg 3>, Section 12: Contract Documents. This implies a need for contractor verification.
Cleaning Requirments | Q100 | What quality assurance/quality control plan requirements are specified? | The document specifies quality assurance requirements for video quality and database standards. "If the quality is not sufficient, re-record the sanitary sewer segment and provide a new video at no additional cost to the City." <PDF pg 150> | 100% | 150 | Found on <PDF pg 150>, Section 1.05: Quality assurance measures ensure accurate and reliable inspection data.
Cleaning Requirments | Q101 | What items are considered inclusive | The document includes degreaser as incidental and requires submission of equipment lists and manuals. "Degreaser for the pipe segments is incidental." <PDF pg 149> | 100% | 149 | Found on <PDF pg 149>, Section 1.02: Clarifies what is included in the contractor's responsibilities without additional payment.

## By Section
Section | Total Questions | Answered | Answer Rate | Avg Confidence
General Project Information | 10 | 10 | 100% | 95%
Televising Requirments | 11 | 2 | 18% | 90%
Access to easement | 10 | 3 | 30% | 100%
Safety & Environmental Compliance | 10 | 7 | 70% | 92%
Equipment & Resource Requirements | 10 | 8 | 80% | 96%
Warranty & Project Closeout | 10 | 9 | 90% | 96%
Special Conditions & Constraints | 10 | 7 | 70% | 76%
Pricing Structure & Payment | 10 | 9 | 90% | 98%
Cleaning Requirments | 11 | 8 | 73% | 91%